## Project Purpose Worksheet
Status Report
Project |  | Status: (Red/Yellow/Green)
Date: | 2022-05-05 | Overall Status: | Green
Contact: | nfang16@uw.edu | Explanation: | All assignments done, it session reviewed multiple times and project up to this point understood
Prepared By: | Nicholas Fang
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Implemented database in Snowflake
Implemented stage tables and initial data load
Shared database and completed module 5 assignments
ID # | Key Issues | Action Plan |  |  | Status
| Implement dimensional models | Starting week of mod5 |  |  | Open
| Model Accuracy | Feedback and revision
Critical Milestones |  | Health | Due Date | Comment/Status
G
Implement initial Snowflake database, stages, and tables |  | G | 2022-05-05 | Completed
Mod6 Review and IT session |  | G | 2022-05-06 | Open
G
G
G
G
G